## WBS
PROJECT WORK BREAKDOWN STRUCTURE
# | Function/Screen | Feature | Level* | Function/Screen Details | Planned | Status
1 | Register User Account | Authentication & Authorization | Simple | Create a new end-user account with validated credentials. | Iteration 1 | Pending
2 | Register Specialist Account | Authentication & Authorization | Medium | Create a specialist account pending administrator verification/approval. | Iteration 1 | Pending
3 | Login | Authentication & Authorization | Simple | Authenticate User, Specialist, or Admin and issue JWT-based access credentials. | Iteration 1 | Pending
4 | Logout | Authentication & Authorization | Simple | End the current authenticated session. | Iteration 1 | Pending
5 | Reset Password | Authentication & Authorization | Simple | Request a password reset using the registered email/account identifier and set a new password after successful verification. | Iteration 1 | Pending
6 | Anonymous Assessment | Authentication & Authorization | Medium | Allow a guest to complete PHQ-9/GAD-7 screening without creating an account. | Iteration 1 | Pending
7 | Authorize Role Access | Authentication & Authorization | Medium | Enforce role-based access for User, Specialist, and Admin. | Iteration 1 | Pending
8 | View User Profile | User Profile & Privacy | Simple | View the authenticated user's profile information. | Iteration 1 | Pending
9 | Update User Profile | User Profile & Privacy | Medium | Update editable personal profile information and preferences. | Iteration 1 | Pending
10 | View Data Consent Settings | User Profile & Privacy | Simple | View current consent choices for sensitive mental-health data processing and specialist access. | Iteration 1 | Pending
11 | Update Data Consent Settings | User Profile & Privacy | Medium | Update consent preferences for AI processing and specialist data access. | Iteration 1 | Pending
12 | Grant Specialist Data Access | User Profile & Privacy | Medium | Grant a selected specialist permission to view specified assessment, trend, or journal data. | Iteration 3 | Pending
13 | Revoke Specialist Data Access | User Profile & Privacy | Simple | Revoke a specialist's previously granted permission to access user data. | Iteration 3 | Pending
14 | Request Personal Data Deletion | User Profile & Privacy | Medium | Request deletion of eligible personal, journal, assessment, and related user data. | Iteration 4 | Pending
15 | Create Emotion Journal Entry | Emotion Journal | Medium | Create a daily emotional journal entry for tracking and AI analysis. | Iteration 1 | Pending
16 | View Journal List | Emotion Journal | Medium | View the user's journal entries ordered by date. | Iteration 1 | Pending
17 | View Journal Entry Details | Emotion Journal | Simple | View the full content and metadata of one journal entry. | Iteration 1 | Pending
18 | Update Emotion Journal Entry | Emotion Journal | Medium | Edit an existing emotional journal entry. | Iteration 1 | Pending
19 | Delete Emotion Journal Entry | Emotion Journal | Simple | Delete a selected journal entry. | Iteration 1 | Pending
20 | Complete PHQ-9 Assessment | Psychological Assessment | Medium | Complete the PHQ-9 psychological screening by answering and submitting all questions. | Iteration 1 | Pending
21 | Complete GAD-7 Assessment | Psychological Assessment | Medium | Complete the GAD-7 psychological screening by answering and submitting all questions. | Iteration 1 | Pending
22 | View Assessment Result | Psychological Assessment | Medium | View one PHQ-9/GAD-7 result with score, screening level, explanation, and disclaimer. | Iteration 1 | Pending
23 | View Assessment History | Psychological Assessment | Medium | View previous PHQ-9/GAD-7 results over time. | Iteration 2 | Pending
24 | Delete Assessment Record | Psychological Assessment | Simple | Delete an eligible assessment record from the user's history. | Iteration 4 | Pending
25 | Analyze Journal with LLM | AI Emotion Analysis | Complex | Analyze Vietnamese journal text using Gemini/OpenAI via prompt engineering. | Iteration 2 | Pending
26 | View Emotion Analysis Result | AI Emotion Analysis | Medium | View sentiment polarity and dominant emotional states detected from a journal entry. | Iteration 2 | Pending
27 | Re-run Emotion Analysis | AI Emotion Analysis | Medium | Reprocess an eligible journal entry when analysis must be regenerated. | Iteration 2 | Pending
28 | Run AI Benchmark Evaluation | AI Model Evaluation | Complex | The admin triggers an evaluation run using the selected dataset to execute model inference and calculate evaluation metrics for comparison. | Iteration 4 | Pending
29 | View AI Model Comparison Result | AI Model Evaluation | Complex | Compare LLM and PhoBERT using Accuracy, Precision, Recall, F1-score, response time, and suitability. | Iteration 4 | Pending
30 | View Risk Classification Result | Risk Classification | Medium | View the current risk level with a screening-focused explanation and non-diagnostic disclaimer. | Iteration 2 | Pending
31 | View Personalized Intervention Plan | Intervention Workflow | Medium | View generated intervention recommendations and suggested next actions. | Iteration 2 | Pending
32 | View Crisis Hotline Information | Emergency Support | Simple | Display crisis-support hotline information for urgent external support. | Iteration 2 | Pending
33 | View Emergency Support Guidance | Emergency Support | Medium | Display guidance encouraging immediate contact with suitable emergency or professional services. | Iteration 2 | Pending
34 | View Self-Help Resource List | Self-Help Resources | Medium | Browse breathing, meditation, wellness, educational video, and journaling resources. | Iteration 2 | Pending
35 | View Self-Help Resource Details | Self-Help Resources | Simple | View content and instructions for one self-help resource. | Iteration 2 | Pending
36 | View Specialist List | Specialist Discovery | Medium | Browse approved specialists available on the platform. | Iteration 3 | Pending
37 | Search Specialists | Specialist Discovery | Medium | Search specialists using supported criteria such as name or specialty. | Iteration 3 | Pending
38 | Filter Specialists | Specialist Discovery | Medium | Filter specialists by specialty, availability, consultation method, rating, or supported criteria. | Iteration 3 | Pending
39 | View Specialist Details | Specialist Discovery | Medium | View specialist profile, expertise, experience, consultation information, rating, and availability summary. | Iteration 3 | Pending
40 | Generate Specialist Recommendation | Specialist Matching | Complex | Recommend suitable specialists based on user needs, risk level, and supported matching criteria. | Iteration 3 | Pending
41 | View Recommended Specialist List | Specialist Matching | Medium | View specialists recommended by the system for the current user. | Iteration 3 | Pending
42 | View Subscription Plans | Subscription & Payment | Medium | View available Free and Premium subscription plans, including price, duration, consultation credits, and included benefits. | Iteration 3 | Pending
43 | View Subscription Details | Subscription & Payment | Simple | View the benefits, consultation credits, price, and validity period of a selected subscription plan. | Iteration 3 | Pending
44 | Subscribe to Premium Plan | Subscription & Payment | Medium | Subscribe to a selected Premium plan and create a pending subscription before payment. | Iteration 3 | Pending
45 | Make Subscription Payment | Subscription & Payment | Medium | Pay for the selected Premium subscription using a supported payment method. | Iteration 3 | Pending
46 | View Payment Status | Subscription & Payment | Simple | View the current status of a subscription payment, such as pending, successful, or failed. | Iteration 3 | Pending
47 | View Subscription Status | Subscription & Payment | Simple | View the user's current subscription status, remaining validity period, and available consultation credits. | Iteration 3 | Pending
48 | View Payment History | Subscription & Payment | Medium | View previous subscription payments and their transaction details. | Iteration 3 | Pending
49 | Cancel Subscription | Subscription & Payment | Medium | Cancel an active subscription or disable its future renewal according to platform policy. | Iteration 3 | Pending
50 | View Consultation Credit Balance | Subscription & Payment | Simple | View the number of unused specialist consultation credits included in the user's active Premium subscription. | Iteration 3 | Pending
51 | View Consultation Credit History | Subscription & Payment | Medium | View the usage history of consultation credits, including redeemed, returned, and expired credits. | Iteration 3 | Pending
52 | View Own Specialist Profile | Specialist Profile | Simple | Allow a specialist to view their own professional profile. | Iteration 3 | Pending
53 | Update Specialist Profile | Specialist Profile | Medium | Update professional biography, specialties, experience, consultation methods, and profile information. | Iteration 3 | Pending
54 | Upload Specialist Verification Document | Specialist Profile | Medium | Upload professional verification documents for administrator review. | Iteration 3 | Pending
55 | View Specialist Verification Status | Specialist Profile | Simple | View current specialist account verification/approval status. | Iteration 3 | Pending
56 | Create Availability Slot | Specialist Availability | Medium | Create a consultation time slot available for booking. | Iteration 3 | Pending
57 | View Availability Slot List | Specialist Availability | Medium | View all availability slots owned by the specialist. | Iteration 3 | Pending
58 | View Availability Slot Details | Specialist Availability | Simple | View details of one availability slot. | Iteration 3 | Pending
59 | Update Availability Slot | Specialist Availability | Medium | Edit an available consultation time slot before booking restrictions apply. | Iteration 3 | Pending
60 | Delete Availability Slot | Specialist Availability | Simple | Remove an eligible availability slot. | Iteration 3 | Pending
61 | View Specialist Available Slots | Specialist Availability | Medium | Allow users to view bookable slots for a selected specialist. | Iteration 3 | Pending
62 | Book Appointment | Appointment Scheduling | Medium | Book an available consultation slot using an available consultation credit from an active Premium subscription. | Iteration 3 | Pending
63 | View User Appointment List | Appointment Scheduling | Medium | View the user's upcoming and previous appointments. | Iteration 3 | Pending
64 | View Specialist Appointment List | Appointment Scheduling | Medium | View appointment requests and scheduled consultations assigned to the specialist. | Iteration 3 | Pending
65 | View Appointment Details | Appointment Scheduling | Medium | View appointment time, participants, consultation method, status, and related information. | Iteration 3 | Pending
66 | Accept Appointment | Appointment Scheduling | Simple | Allow the specialist to accept a pending appointment request. | Iteration 3 | Pending
67 | Reject Appointment | Appointment Scheduling | Simple | Allow the specialist to reject a pending appointment request and return the reserved consultation credit. | Iteration 3 | Pending
68 | Cancel Appointment by User | Appointment Scheduling | Simple | Allow the user to cancel an eligible appointment according to the cancellation policy. | Iteration 3 | Pending
69 | Cancel Appointment by Specialist | Appointment Scheduling | Simple | Allow the specialist to cancel an eligible appointment and return the user's consultation credit. | Iteration 3 | Pending
70 | Reschedule Appointment Request | Appointment Scheduling | Medium | Request a new time for an eligible appointment. | Iteration 3 | Pending
71 | Confirm Rescheduled Appointment | Appointment Scheduling | Simple | Confirm an approved rescheduled appointment time. | Iteration 3 | Pending
72 | Mark Appointment as Completed | Appointment Scheduling | Simple | Allow the specialist to mark a completed consultation session and consume the associated consultation credit. | Iteration 3 | Pending
73 | View Appointment History | Appointment Scheduling | Medium | View completed, cancelled, rejected, and previous appointments. | Iteration 3 | Pending
74 | Create Consultation Conversation | Real-Time Chat | Medium | Create a private conversation for an eligible User-Specialist relationship or confirmed appointment. | Iteration 3 | Pending
75 | View Conversation List | Real-Time Chat | Medium | View all active and previous specialist-user conversations available to the authenticated account. | Iteration 3 | Pending
76 | View Conversation Details | Real-Time Chat | Medium | Open one conversation and load its message history. | Iteration 3 | Pending
77 | Send Text Message | Real-Time Chat | Medium | Send a text message to the other participant in real time. | Iteration 3 | Pending
78 | Receive Real-Time Message | Real-Time Chat | Medium | Receive newly sent messages without manually refreshing the conversation. | Iteration 3 | Pending
79 | Mark Message as Read | Real-Time Chat | Simple | Update message read status when the recipient views the conversation. | Iteration 3 | Pending
80 | Delete Own Message | Real-Time Chat | Simple | Allow a sender to delete an eligible message according to platform policy. | Iteration 3 | Pending
81 | Close Consultation Conversation | Real-Time Chat | Simple | Close or archive an eligible consultation conversation after the relationship/session ends. | Iteration 3 | Pending
82 | Report Chat Message | Real-Time Chat | Simple | Report an inappropriate or unsafe message for administrator moderation. | Iteration 3 | Pending
83 | Create Specialist Review | Specialist Reviews | Medium | Allow a user with an eligible completed appointment to submit a rating and optional review comment. | Iteration 3 | Pending
84 | View Specialist Review List | Specialist Reviews | Medium | View reviews and ratings submitted for a specialist. | Iteration 3 | Pending
85 | View Specialist Review Details | Specialist Reviews | Simple | View the full content and metadata of one specialist review. | Iteration 3 | Pending
86 | Update Specialist Review | Specialist Reviews | Medium | Allow the review author to edit an eligible specialist review. | Iteration 3 | Pending
87 | Delete Specialist Review | Specialist Reviews | Simple | Allow the review author to delete an eligible specialist review. | Iteration 3 | Pending
88 | Report Specialist Review | Specialist Reviews | Simple | Report an inappropriate specialist review for moderation. | Iteration 3 | Pending
89 | Create Follow-up Plan | Follow-up & Monitoring | Medium | Create follow-up milestones after intervention or completed specialist consultation. | Iteration 3 | Pending
90 | View Follow-up Plan | Follow-up & Monitoring | Simple | View upcoming follow-up milestones and required actions. | Iteration 3 | Pending
91 | Update Follow-up Plan | Follow-up & Monitoring | Medium | Adjust eligible follow-up dates or reminder preferences. | Iteration 3 | Pending
92 | Submit Follow-up Check-in | Follow-up & Monitoring | Medium | Record current emotional state and progress after intervention or consultation. | Iteration 3 | Pending
93 | Start Follow-up Assessment | Follow-up & Monitoring | Simple | Start a repeated PHQ-9/GAD-7 assessment at a follow-up milestone. | Iteration 3 | Pending
94 | View Progress Comparison | Follow-up & Monitoring | Complex | Compare emotional indicators, risk levels, and repeated assessment scores over time. | Iteration 3 | Pending
95 | View Notification List | Notifications | Medium | View assessment reminders, appointment updates, chat notifications, follow-up notices, subscription updates, and alerts. | Iteration 3 | Pending
96 | View Notification Details | Notifications | Simple | View the full content of one notification. | Iteration 3 | Pending
97 | Mark Notification as Read | Notifications | Simple | Change a notification status from unread to read. | Iteration 3 | Pending
98 | View Emotional Dashboard | Analytics | Complex | View personal emotional trends, assessment history, risk evolution, and follow-up progress. | Iteration 1 | Pending
99 | View Mood / Emotion Trend | Analytics | Medium | View journal-derived emotional indicators by supported time period. | Iteration 4 | Pending
100 | View Assessment Trend | Analytics | Medium | View PHQ-9/GAD-7 score changes across repeated assessments. | Iteration 4 | Pending
101 | Filter Analytics by Period | Analytics | Simple | Filter personal analytics by supported day/week/month date ranges. | Iteration 4 | Pending
102 | View Specialist Dashboard | Specialist Portal | Complex | View appointment workload, upcoming sessions, unread chats, permitted user summaries, and earnings information. | Iteration 4 | Pending
103 | View Consenting User List | Specialist Portal | Medium | View users who have explicitly granted the specialist access to selected data. | Iteration 4 | Pending
104 | View Consenting User Details | Specialist Portal | Complex | View permitted user assessment history, emotional trends, risk summaries, and allowed journal data. | Iteration 4 | Pending
105 | View User Assessment History as Specialist | Specialist Portal | Medium | View assessment history of a user who granted the required permission. | Iteration 4 | Pending
106 | View User Emotional Trend as Specialist | Specialist Portal | Medium | View emotional trend data of a consenting user. | Iteration 4 | Pending
107 | View User Journal Data as Specialist | Specialist Portal | Complex | View only journal entries explicitly available under the user's consent settings. | Iteration 4 | Pending
108 | View Specialist Earnings | Specialist Portal | Medium | View earnings generated from completed specialist consultations. | Iteration 4 | Pending
109 | View Specialist Payout History | Specialist Portal | Medium | View completed and previous payouts from eligible specialist consultations. | Iteration 4 | Pending
110 | View Pending Payout | Specialist Portal | Simple | View earnings that are pending settlement before being paid to the specialist. | Iteration 4 | Pending
111 | Admin Login | Administration | Simple | Authenticate an administrator and enforce Admin permissions. | Iteration 4 | Pending
112 | View Admin Dashboard | Administration | Complex | View platform-level users, specialists, subscriptions, payments, appointments, reviews, activity, risk indicators, and operational summaries. | Iteration 4 | Pending
113 | View User List (Admin) | Admin - Users | Medium | View and search registered user accounts. | Iteration 4 | Pending
114 | View User Details (Admin) | Admin - Users | Medium | View permitted account and system-status information for one user. | Iteration 4 | Pending
115 | Update User Account Status | Admin - Users | Medium | Change allowed administrative account status fields such as active or disabled. | Iteration 4 | Pending
116 | Delete User Account | Admin - Users | Medium | Delete a user account according to authorization and retention rules. | Iteration 4 | Pending
117 | View Specialist List (Admin) | Admin - Specialists | Medium | View and search specialist accounts and verification statuses. | Iteration 4 | Pending
118 | View Specialist Details (Admin) | Admin - Specialists | Medium | View specialist profile and submitted verification information. | Iteration 4 | Pending
119 | Approve Specialist Account | Admin - Specialists | Medium | Approve a specialist account after verification review. | Iteration 4 | Pending
120 | Reject Specialist Account | Admin - Specialists | Medium | Reject a specialist account or verification request with an administrative reason. | Iteration 4 | Pending
121 | Update Specialist Account Status | Admin - Specialists | Medium | Change an approved specialist account's administrative status. | Iteration 4 | Pending
122 | Delete Specialist Account | Admin - Specialists | Medium | Delete an eligible specialist account according to platform rules. | Iteration 4 | Pending
123 | View Subscription List (Admin) | Admin - Subscriptions & Payments | Medium | View user subscriptions, plans, statuses, and validity periods. | Iteration 4 | Pending
124 | View Subscription Details (Admin) | Admin - Subscriptions & Payments | Medium | View administrative details of a selected user subscription. | Iteration 4 | Pending
125 | View Payment List (Admin) | Admin - Subscriptions & Payments | Medium | View subscription payment transactions and their statuses for operational monitoring. | Iteration 4 | Pending
126 | View Payment Details (Admin) | Admin - Subscriptions & Payments | Simple | View administrative details of one subscription payment transaction. | Iteration 4 | Pending
127 | View Specialist Payout List (Admin) | Admin - Specialist Payouts | Medium | View specialist payout records, amounts, statuses, and settlement information. | Iteration 4 | Pending
128 | View Specialist Payout Details (Admin) | Admin - Specialist Payouts | Simple | View details of one specialist payout. | Iteration 4 | Pending
129 | Process Specialist Payout | Admin - Specialist Payouts | Medium | Process an eligible payout to a specialist after completed consultations and settlement validation. | Iteration 4 | Pending
130 | Create Self-Help Resource | Admin - Self-Help Content | Medium | Create a breathing, meditation, wellness, educational, or journaling resource. | Iteration 4 | Pending
131 | View Self-Help Resource List (Admin) | Admin - Self-Help Content | Medium | View and search all self-help resources for administration. | Iteration 4 | Pending
132 | View Self-Help Resource Details (Admin) | Admin - Self-Help Content | Simple | View all fields of one self-help resource. | Iteration 4 | Pending
133 | Update Self-Help Resource | Admin - Self-Help Content | Medium | Edit self-help resource content, category, visibility, or metadata. | Iteration 4 | Pending
134 | Delete Self-Help Resource | Admin - Self-Help Content | Simple | Delete an obsolete self-help resource. | Iteration 4 | Pending
135 | Create Hotline Information | Admin - Hotlines | Simple | Add a crisis/support hotline record. | Iteration 4 | Pending
136 | View Hotline List (Admin) | Admin - Hotlines | Simple | View all hotline records maintained by the platform. | Iteration 4 | Pending
137 | View Hotline Details (Admin) | Admin - Hotlines | Simple | View all stored information for one hotline record. | Iteration 4 | Pending
138 | Update Hotline Information | Admin - Hotlines | Simple | Edit hotline contact information or descriptive guidance. | Iteration 4 | Pending
139 | Delete Hotline Information | Admin - Hotlines | Simple | Remove an obsolete hotline record. | Iteration 4 | Pending
140 | View Reported Review List | Admin - Review Moderation | Medium | View specialist reviews reported by users or specialists. | Iteration 4 | Pending
141 | View Reported Review Details | Admin - Review Moderation | Medium | View review content, report reason, and moderation context. | Iteration 4 | Pending
142 | Hide Specialist Review | Admin - Review Moderation | Simple | Hide a review that violates platform policy. | Iteration 4 | Pending
143 | Restore Specialist Review | Admin - Review Moderation | Simple | Restore a previously hidden review when appropriate. | Iteration 4 | Pending
144 | Delete Specialist Review as Admin | Admin - Review Moderation | Simple | Permanently remove a review according to moderation policy. | Iteration 4 | Pending
145 | View Reported Chat Message List | Admin - Chat Moderation | Medium | View chat messages reported for moderation. | Iteration 4 | Pending
146 | View Reported Chat Message Details | Admin - Chat Moderation | Medium | View a reported message and relevant moderation metadata under platform policy. | Iteration 4 | Pending
147 | Take Action on Reported Chat Message | Admin - Chat Moderation | Medium | Apply the configured moderation action to a reported chat message or involved account. | Iteration 4 | Pending
148 | View Platform Appointment List | Admin - Appointments | Complex | View platform-wide appointments and their current statuses for operational monitoring. | Iteration 4 | Pending
149 | View Platform Appointment Details | Admin - Appointments | Medium | View one appointment's administrative metadata without exposing unnecessary sensitive user data. | Iteration 4 | Pending
150 | Import Evaluation Dataset | Admin - Dataset & Evaluation | Complex | Import and validate a Vietnamese emotional dataset or evaluation sample. | Iteration 4 | Pending
151 | View Evaluation Dataset List | Admin - Dataset & Evaluation | Medium | View datasets prepared for AI benchmarking. | Iteration 4 | Pending
152 | View Evaluation Dataset Details | Admin - Dataset & Evaluation | Medium | View dataset metadata, source information, size, and preprocessing status. | Iteration 4 | Pending
153 | Update Dataset Metadata | Admin - Dataset & Evaluation | Medium | Update editable dataset metadata and evaluation configuration. | Iteration 4 | Pending
154 | Delete Evaluation Dataset | Admin - Dataset & Evaluation | Medium | Remove an eligible evaluation dataset. | Iteration 4 | Pending
155 | Run AI Benchmark Evaluation | Admin - Dataset & Evaluation | Complex | Run configured LLM/PhoBERT evaluation on the selected dataset. | Iteration 4 | Pending
156 | View Benchmark Evaluation Results | Admin - Dataset & Evaluation | Complex | View Accuracy, Precision, Recall, F1-score, response time, and model comparison results. | Iteration 4 | Pending
157 | View System Activity Report | Admin - Reporting | Complex | View platform operational and user-activity reporting information. | Iteration 4 | Pending
158 | View Platform Trend Analysis | Admin - Reporting | Complex | View aggregated screening, risk, subscription, payment, appointment, and emotional indicators over time. | Iteration 4 | Pending
159 | View Audit Log | Admin - Security & Privacy | Medium | View access, consent, security, subscription, payment, appointment, and data-related audit events. | Iteration 4 | Pending
160 | Filter Audit Log | Admin - Security & Privacy | Simple | Filter audit events by date, action type, actor, or supported criteria. | Iteration 4 | Pending
161 | Configure Data Retention Policy | Admin - Security & Privacy | Medium | Create or update data-retention settings for supported sensitive-data categories. | Iteration 4 | Pending
162 | View Data Retention Policy | Admin - Security & Privacy | Simple | View currently configured data-retention rules. | Iteration 4 | Pending
(*) You can rate the functions' complexity based on the number of fields on the screens or the number of transactions in the function, with the details as below
| simple | <=7 fields | <=3 transactions
| medium | <=15 fields | <= 7 transactions
| complex | >15 fields | > 7 transactions
In which:
fields: screen components or database table fields
transactions: action buttons, user or database transactions
# | Function/Screen | Assignee
1 | UC-01 Authentication & User Management | Khôi
2 | UC-02 Mental Health Assessment & AI Analysis | Khôi
3 | UC-03 Intervention & Support | Nguyên
4 | UC-04 Specialist Discovery & Appointment | Quyên
5 | UC-05 Communication & Follow-up | Thảo
6 | UC-06 Specialist Portal | Quyên
7 | UC-07 Administration | Vũ

## Flow
Actor | Main Modules
User | Authentication, Profile & Consent, Journal, PHQ-9/GAD-7, AI Results, Risk/Intervention, Specialist Discovery, Appointment, Chat, Reviews, Follow-up, Analytics
Specialist | Authentication, Specialist Profile, Verification Status, Availability Slots, Appointment Handling, Real-Time Chat, Consented User Data, Reviews Received
Admin | User Administration, Specialist Approval, Content/Hotline CRUD, Review Moderation, Chat Moderation, Appointment Monitoring, Dataset/Evaluation, Reporting, Audit & Retention
Actor / Flow | Main Flow
Anonymous | Landing → PHQ-9/GAD-7 → Result → Risk Level → Basic Recommendation → Optional Register/Login
User | Assessment / Journal → AI Analysis → Risk Classification → Recommendation → Specialist → Booking → Consent → Chat → Consultation → Review → Follow-up
Specialist | Register → Verification → Admin Approval → Dashboard → Appointment → Consented User Data → Chat → Consultation → Complete → Reviews
Admin | Login → Dashboard → Users / Specialists / Content / Reviews / Chat Reports / Appointments / Analytics / Audit Log

## Issues
PROJECT ISSUES
# | Issue | Potential Impact | Priority | Owner | Open Date | Close Date | Status | Notes
1 |  |  | Medium | HuyNMG |  |  | Open
2 |  |  | Medium | HuyNMG |  |  | Open
3 |  |  | Medium | HuyNG |  |  | Open
4 |  |  | Medium | HuyNG |  |  | Open
5 |  |  | Medium | HuyNG |  |  | Open
6 |  |  | Medium | DucBH |  |  | Open
7 |  |  | Medium | HuyLQ |  |  | Open

## Defects
PROJECT DEFECTS
Feature | Function/Screen | Tester | Defect Description | Assign To | Status | Notes
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending

## Q&A
PROJECT Q&A
Date | Question | By | Priority | Status | Note (answer, other notes)
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open